## Vendors
VendorID | VendorName | Location | Contact1Name | Contact1Email | Contact2Name | Contact2Email | CreatedAt
VEN-0001 | Taizhou Toplong Electrical & Mech | Taizhou, China |  |  |  |  | 2024-01-01

## PurchaseOrders
POID | VendorID | Project | PONo | PODescription | Quantity | ContractDeliveryDate | ForecastDeliveryDate | ReportNo | ReportDate | CreatedAt
PO-0001 | VEN-0001 | [6 empty] | Rev 0 | 2024-01-01 | 2024-01-01

## Milestones
MilestoneID | POID | Activity | DetailActivity | PlanStart | PlanFinish | ActualStart | ActualFinish | WeightFactor | LastProgress | ThisProgress | AchievedPercent | DetailsAchieved
MS-0001 | PO-0001 | PO Issue | Purchase Order |  |  |  |  | 1 | 0 | 0 | 0
MS-0002 | PO-0001 | KOM | Kick-off Meeting |  |  |  |  | 1 | 0 | 0 | 0
MS-0003 | PO-0001 | Engineering | Issue of Vendor Data |  |  |  |  | 5 | 0 | 0 | 0
MS-0004 | PO-0001 | Engineering | Approval of Vendor Data |  |  |  |  | 5 | 0 | 0 | 0
MS-0005 | PO-0001 | Material | Order of Major Materials |  |  |  |  | 10 | 0 | 0 | 0
MS-0006 | PO-0001 | Material | Receipt of Major Materials |  |  |  |  | 15 | 0 | 0 | 0
MS-0007 | PO-0001 | PIM | Pre-Inspection Meeting |  |  |  |  | 3 | 0 | 0 | 0
MS-0008 | PO-0001 | Fabrication & Inspection | Pre-Activity (Fit-up / Components Fabrication) |  |  |  |  | 10 | 0 | 0 | 0
MS-0009 | PO-0001 | Fabrication & Inspection | Main Activity (Welding / Final Assembly) |  |  |  |  | 20 | 0 | 0 | 0
MS-0010 | PO-0001 | Fabrication & Inspection | Final Inspection |  |  |  |  | 10 | 0 | 0 | 0
MS-0011 | PO-0001 | Fabrication & Inspection | Inspection Release Note (IRN) |  |  |  |  | 5 | 0 | 0 | 0
MS-0012 | PO-0001 | Packing & Shipping | Item Packing List (BOM) |  |  |  |  | 3 | 0 | 0 | 0
MS-0013 | PO-0001 | Packing & Shipping | Shipping Data (Invoice/Packing List/CO/CQ) |  |  |  |  | 2 | 0 | 0 | 0
MS-0014 | PO-0001 | FOB/DDP/FOT | Item Delivered |  |  |  |  | 10 | 0 | 0 | 0

## SCurve
SCurveID | POID | PeriodLabel | PlanDate | ActualDate | PlanPercent | ActualPercent
SC-0001 | PO-0001 | Period 1 | 2024-01-31 | 2024-01-31 | 0 | 0.01

## Documents
DocID | POID | DocumentNo | DocumentTitle | Revision | DocumentStatus | PlanSubmissionDate | PlanApprovalDate | ActualSubmissionDate | ActualApprovalDate | Remark
DOC-0001 | PO-0001 |  | General Arrangement Drawing | 0 | Open

## SubVendor
ItemID | POID | Description | Specification | Size | QtyRequired | Units | POIssuancePlanDate | POIssuanceActualDate | SubPONo | Manufacturer | CountryOfOrigin | ETDCOO | DeliveryMode | ETAShop | ArrivalDate | ArrivalQty | Balance | Remarks
ITM-0001 | PO-0001 | Raw Material (SS Plate) |  |  | 1 | lot | [6 empty] | Sea |  |  | 0 | 1

## Users
Username | PasswordHash | PasswordSalt | Role | VendorID | Name | CreatedAt
admin | 457d15bb939d5cdb49a4cb2b8aaa12d434f06f52ba6404b7e27c02553f4936d4 | admin-salt-2024 | Admin |  | Administrator | 2024-01-01
vendor1 | 313e4af96668454ca7aed47ac312a1927384b1bb3fc62ff62a15c02bce647499 | vendor-salt-2024 | Vendor | VEN-0001 | Taizhou Toplong | 2024-01-01
viewer | feb9db79e0f9eaf646f823ef8136f134ec1ac489cf0c422d92b7bcc18470a865 | viewer-salt-2024 | User |  | Viewer | 2024-01-01